## Gantt Chart
Yosemite - The Stefano Shop Digital Transformation
Project Manager | Hashim Naveed |  | Estimated Completion | 2026-08-07
Start Date | 2026-06-08 |  | Methodology | Waterfall
Phase | Task Title | Task Owner | Start Date | Due Date | Duration | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9
[6 empty] | Mon 06/08 | Tue 06/09 | Wed 06/10 | Thu 06/11 | Fri 06/12 | Mon 06/15 | Tue 06/16 | Wed 06/17 | Thu 06/18 | Fri 06/19 | Mon 06/22 | Tue 06/23 | Wed 06/24 | Thu 06/25 | Fri 06/26 | Mon 06/29 | Tue 06/30 | Wed 07/01 | Thu 07/02 | Fri 07/03 | Mon 07/06 | Tue 07/07 | Wed 07/08 | Thu 07/09 | Fri 07/10 | Mon 07/13 | Tue 07/14 | Wed 07/15 | Thu 07/16 | Fri 07/17 | Mon 07/20 | Tue 07/21 | Wed 07/22 | Thu 07/23 | Fri 07/24 | Mon 07/27 | Tue 07/28 | Wed 07/29 | Thu 07/30 | Fri 07/31 | Mon 08/03 | Tue 08/04 | Wed 08/05 | Thu 08/06 | Fri 08/07
Initiation | Kickoff meeting | Project Manager | 2026-06-08 | 2026-06-08 | 1 | bar: Week 1 Mon 06/08
Initiation | Engage stakeholders | Project Manager | 2026-06-08 | 2026-06-12 | 5 | bar: Week 1 Mon 06/08 to Week 1 Fri 06/12
Initiation | Status Report 1 | Project Manager | 2026-06-19 | 2026-06-19 | 1 | bar: Week 2 Fri 06/19
Delivery | Create social media channels | Taylor | 2026-06-08 | 2026-06-12 | 5 | bar: Week 1 Mon 06/08 to Week 1 Fri 06/12
Delivery | Build storefront | Aliyah | 2026-06-08 | 2026-06-19 | 10 | bar: Week 1 Mon 06/08 to Week 2 Fri 06/19
Documentation | Storefront Technical Documentation | Aliyah | 2026-06-18 | 2026-06-19 | 2 | bar: Week 2 Thu 06/18 to Week 2 Fri 06/19
Delivery | Input Inventory Data | Moe | 2026-06-22 | 2026-06-26 | 5 | bar: Week 3 Mon 06/22 to Week 3 Fri 06/26
Documentation | Platform user's manual | Moe | 2026-06-26 | 2026-06-30 | 3 | bar: Week 3 Fri 06/26 to Week 4 Tue 06/30
Delivery | Build social media integration | Aliyah | 2026-06-22 | 2026-07-03 | 10 | bar: Week 3 Mon 06/22 to Week 4 Fri 07/03
Delivery | Build recommendation engine | Aliyah | 2026-07-06 | 2026-07-17 | 10 | bar: Week 5 Mon 07/06 to Week 6 Fri 07/17
Documentation | Recommendation Engine Documentation | Aliyah | 2026-07-16 | 2026-07-17 | 2 | bar: Week 6 Thu 07/16 to Week 6 Fri 07/17
Delivery | Create Custom Sales Report | Moe | 2026-07-13 | 2026-07-17 | 5 | bar: Week 6 Mon 07/13 to Week 6 Fri 07/17
Reporting | Status Report 2 (Inventory Risk) | Project Manager | 2026-06-22 | 2026-06-22 | 1 | bar: Week 3 Mon 06/22
Reporting | Status Report 3 | Project Manager | 2026-07-17 | 2026-07-17 | 1 | bar: Week 6 Fri 07/17
Training & Launch | Train Stefano's on platform | Moe | 2026-07-20 | 2026-07-24 | 5 | bar: Week 7 Mon 07/20 to Week 7 Fri 07/24
Training & Launch | Final QA and Go-Live Readiness | Aliyah | 2026-07-27 | 2026-07-31 | 5 | bar: Week 8 Mon 07/27 to Week 8 Fri 07/31
Training & Launch | Knowledge transfer and Q&A | Project Manager / Moe | 2026-07-27 | 2026-07-29 | 3 | bar: Week 8 Mon 07/27 to Week 8 Wed 07/29
Training & Launch | Release / Go-Live | Aliyah | 2026-08-03 | 2026-08-03 | 1 | bar: Week 9 Mon 08/03
Closure | Lessons Learned Document | Project Manager | 2026-08-06 | 2026-08-07 | 2 | bar: Week 9 Thu 08/06 to Week 9 Fri 08/07
Closure | Closure meeting | Project Manager | 2026-08-07 | 2026-08-07 | 1 | bar: Week 9 Fri 08/07
Closure | Status Report 4 / Final update | Project Manager | 2026-08-07 | 2026-08-07 | 1 | bar: Week 9 Fri 08/07

## Task Detail
Phase | Task | Assignee | Start | Due | Duration (workdays) | Dependencies / Notes
Initiation | Kickoff meeting | Project Manager | 2026-06-08 | 2026-06-08 | 1
Initiation | Engage stakeholders | Project Manager | 2026-06-08 | 2026-06-12 | 5
Initiation | Status Report 1 | Project Manager | 2026-06-19 | 2026-06-19 | 1
Delivery | Create social media channels | Taylor | 2026-06-08 | 2026-06-12 | 5 | Must finish before Engineering starts social media integration.
Delivery | Build storefront | Aliyah | 2026-06-08 | 2026-06-19 | 10 | Enables inventory data input and storefront documentation.
Documentation | Storefront Technical Documentation | Aliyah | 2026-06-18 | 2026-06-19 | 2
Delivery | Input Inventory Data | Moe | 2026-06-22 | 2026-06-26 | 5 | Depends on customer inventory list; planned date used for Scenario 1 status report.
Documentation | Platform user's manual | Moe | 2026-06-26 | 2026-06-30 | 3
Delivery | Build social media integration | Aliyah | 2026-06-22 | 2026-07-03 | 10 | Depends on social media channels.
Delivery | Build recommendation engine | Aliyah | 2026-07-06 | 2026-07-17 | 10 | Two-week planned scope; Scenario 2 describes possible change request.
Documentation | Recommendation Engine Documentation | Aliyah | 2026-07-16 | 2026-07-17 | 2
Delivery | Create Custom Sales Report | Moe | 2026-07-13 | 2026-07-17 | 5
Reporting | Status Report 2 (Inventory Risk) | Project Manager | 2026-06-22 | 2026-06-22 | 1
Reporting | Status Report 3 | Project Manager | 2026-07-17 | 2026-07-17 | 1
Training & Launch | Train Stefano's on platform | Moe | 2026-07-20 | 2026-07-24 | 5 | Must occur before go-live.
Training & Launch | Final QA and Go-Live Readiness | Aliyah | 2026-07-27 | 2026-07-31 | 5
Training & Launch | Knowledge transfer and Q&A | Project Manager / Moe | 2026-07-27 | 2026-07-29 | 3
Training & Launch | Release / Go-Live | Aliyah | 2026-08-03 | 2026-08-03 | 1 | Final release after QA/readiness and customer training.
Closure | Lessons Learned Document | Project Manager | 2026-08-06 | 2026-08-07 | 2
Closure | Closure meeting | Project Manager | 2026-08-07 | 2026-08-07 | 1
Closure | Status Report 4 / Final update | Project Manager | 2026-08-07 | 2026-08-07 | 1

## Summary
Project | Yosemite - The Stefano Shop Digital Transformation
Methodology | Waterfall
Project Budget | 15000
Promised Revenue Increase | 36000
Discount Rate | 20%
Present Value of Benefit | 30000
Cost-Benefit Ratio | 2
Minimum Schedule | 8 weeks
Maximum Schedule | 12 weeks
Planned Schedule | 9 weeks (June 8 - August 7, 2026)
Status Report 1 | June 19, 2026
Status Report 2 | June 22, 2026 (inventory risk report date)
Status Report 3 | July 17, 2026
Final Status Report | August 7, 2026